ANNEX D TO THE CSR PROPOSAL — KATLABODI INTEGRATED VILLAGE DEVELOPMENT PROJECT

Project 1 — Biodiversity and Medicinal Agroforestry

The Katlabodi hub site: livelihoods, fodder and ecosystem services in a drought year

| Project area | Katlabodi, Murli and Dhankundav — Gram Panchayat Katlabodi, Katol Block, Nagpur District, Maharashtra |
| --- | --- |
| Lead organisation | Ayurvan Foundation |
| Partners | Gram Panchayat Katlabodi (community partner); UrjaGram Innovations Pvt Ltd (framework, technology and development partner) |
| Primary participants | 30–50 women from self-help groups in the pilot, led by the four-member Van Sakhi cadre; small and marginal farmers; livestock-owning households; rural youth |
| Hub site | About 5 ha: 1 ha nursery; 0.5 ha woody medicinal species; 0.5 ha fruit species; 1 ha medicinal shrubs; 2 ha fodder grass; 600 bamboo on the boundary |
| Period | Five years. Year 1 (CSR grant): establishment and demonstration. Years 2–3: supply and extension across the Katol cluster. Years 4–5: enterprise and a State-ready model |
| Year-1 cost to the grant | ₹1,81,46,200 — capital ₹1,65,06,000 and year-one operating shortfall ₹16,40,200 (budget line D) |

# 1. Summary

Project 1 establishes a community-owned, market-linked medicinal agroforestry system at Katlabodi, combining short-duration medicinal and aromatic crops with woody, fruit and fodder species. It is the physical anchor of the Katlabodi hub: its nursery supplies planting material to the Katol cluster and to VB-G RAM G plantation works, and its demonstration plots show what drought-resilient land use looks like on small and marginal holdings.

Within the UrjaGram Sustainable Development Framework (USDF), Project 1 is the nature-based foundation on which the other projects draw: fodder for Project 3, soil moisture and cover that support Project 2, biomass and slurry cycles with Project 4, local food and medicinal knowledge for Project 5, and sequestration data for Project 6. It runs on VanaGram OS, the DEVTech agroforestry module, and is delivered by the Van Sakhi cadre and the women they lead.

The integrated model:

Land → Nursery → Medicinal crops → Agroforestry and fodder → Women-led enterprise → Processing → Market → Income, fodder, biodiversity and carbon

# 2. Why now: the drought and the land

The September 2026 drought declaration covers 265 of Maharashtra’s 358 talukas, with Vidarbha worst affected and Nagpur district among the six worst-hit districts. In a drought year the Katlabodi pattern tightens at once: fodder runs out, the herd leans harder on the 416 hectares of forest, groundwater-fed cropping fails, and household income falls with it. Conventional cropping is exposed to rainfall variability, water stress, input costs and uncertain prices.

Tree-based and medicinal systems spread that risk. Perennial species hold soil and moisture through dry spells; short-duration medicinal crops give early income while trees establish; fodder trees and grasses buffer the herd; and processing and grading add value that stays with women’s groups. IPBES finds that agroforestry benefits are greatest in semi-arid areas and that agroecological options score positively across biodiversity, water, food, health and climate (IPBES Nexus Assessment, Ch. 5.5 and Fig. 5.6.3).

Timing. Nursery stock must be raised between February and May 2027 for planting with the 2027 monsoon. Sanction by December 2026 keeps that window; a later start moves first planting to 2028.

# 3. Biodiversity as infrastructure

Project 1 treats biodiversity the way a panchayat treats a road or a water scheme: as infrastructure that delivers services and must be registered, maintained and financed.

| Infrastructure practice | At Katlabodi |
| --- | --- |
| Asset register | The People’s Biodiversity Register (PBR), updated by the Van Sakhi cadre and maintained on VanaGram OS rather than as a static document |
| Services delivered | Fodder, water regulation, medicinal plants, fuel, pollination and carbon — from the hub site and the 416 ha of forest |
| Condition monitoring | Survival, species diversity and forest-condition records collected by the cadre |
| Maintenance budget | The Local Biodiversity Fund of the Biodiversity Management Committee (BMC), including collection fees it may levy under the Biological Diversity Act |
| Investment plan | Biodiversity projects written into the Gram Panchayat Integrated Investment Plan and the Viksit Gram Panchayat Plan |
| Failure event | A drought year — when services fail, fodder, water and income fail with them |

Most BMCs nationally exist on paper, without funds or a used register. Katlabodi offers the National Biodiversity Authority and the Maharashtra State Biodiversity Board a working BMC, aligned with India’s updated National Biodiversity Strategy and Action Plan (2024). One limit is stated plainly: since the 2023 amendment to the Biological Diversity Act and the 2025 benefit-sharing regulations, users of cultivated medicinal plants are exempt from benefit-sharing, so sales from the hub site do not generate benefit-sharing income. The case rests on ecosystem services and a working BMC, not on benefit-sharing revenue.

# 4. Site and land

Katlabodi village is the primary demonstration site and community hub; Murli and Dhankundav participate through cultivation and livelihood-linked plantation. Land may come from Gram Panchayat land (subject to permission), community land where legally permissible, farmer-owned land, self-help group plots and institutional demonstration plots.

| Component | Area | Purpose |
| --- | --- | --- |
| Nursery | 1 ha | Planting material for the hub, the Katol cluster and VB-G RAM G plantation works |
| Woody medicinal species | 0.5 ha | Long-duration medicinal value, biodiversity and carbon |
| Fruit-bearing species | 0.5 ha | Market income and nutrition |
| Medicinal shrubs | 1 ha | Short-duration income while trees establish |
| Fodder grass | 2 ha | Fodder security for Project 3 |
| Boundary bamboo | 600 trees | Biomass, livelihood, soil protection and a living fence |
| Processing area | Within site | Drying, grading and packing |

Land category decides the rules. Private farmland, Gram Panchayat land, forest land and the three uninhabited Rithi villages fall under different rules. Parcels are finalised only after joint site assessment, land-status verification, and soil and water assessment. Where forest land or community forest resources are involved, the Forest Rights Act and the Forest Department’s management arrangements apply [verify the management status of the 416 ha].

# 5. Design

## 5.1 Species portfolio

A diversified portfolio rather than a single crop. The costed portfolio in the financial model is:

| Group | Species | Primary function |
| --- | --- | --- |
| Woody medicinal | Amla, bael, hirda, moringa | Medicinal value, fruit, nutrition, biodiversity and carbon |
| Fruit-bearing | Mango, sitaphal, mulberry, lemon, jamun, ber, karvanda | Direct sale and products |
| Medicinal shrubs | Ashwagandha, kalmegh, gulab, aloe vera, brahmi | Herbal and Ayurvedic market; early income |
| Fodder | Perennial and seasonal fodder grass | Year-round fodder; less pressure on forest |
| Boundary | Bamboo | Biomass and livelihood from year six |
| Candidates | Lemongrass, safed musli, arjuna | Subject to market demand, agronomic suitability and site assessment |

Selection depends on soil, rainfall, water availability, agronomic suitability and confirmed market demand. Native, low-water-use species are preferred.

## 5.2 Fodder

Fodder species are chosen for local agro-climate, herd size, water availability, palatability, nutrition, regeneration and farmer acceptance. Expected results: year-round fodder, less dependence on purchased fodder, less pressure on natural vegetation, better livestock productivity and productive use of fallow land — directly addressing the panchayat’s fodder deficit of about 2,000 tonnes a year.

## 5.3 Drought-proofing

- Water budget first. Irrigation from the borewell follows the panchayat water budget prepared under Project 2; drip irrigation is used throughout.

- Recharge before extraction. Recharge works on and around the site are sought through VB-G RAM G convergence in the dry season.

- Survival standards. Survival and diversity are measured for at least three to five years, not seedlings planted.

- Stress-tested finances. The financial model tests a drought in year two (section 10).

## 5.4 Market first, cultivation second

Before large-scale cultivation of any high-value crop, the project confirms market demand, buyer specifications, quality requirements, expected price, quantity, harvest season, processing needs and logistics. Produce moves from self-help groups or a producer organisation, through aggregation and primary processing, to Manas Ayurved as anchor buyer, and to Ayurvedic manufacturers, herbal-product companies, essential-oil processors and institutional buyers. A second buyer is developed to avoid dependence on one purchaser.

# 6. Women at the core

Women are the operators of the enterprise, not only its beneficiaries. The four Van Sakhi — two from Katlabodi and one each from Murli and Dhankundav — lead a pilot group of 30–50 women across the chain:

Nursery → Land preparation → Cultivation → Good agricultural practice → Harvest → Primary processing → Drying → Grading → Packing → Aggregation → Market

Selected members progress to master trainers, nursery managers, cultivation coordinators, quality-control representatives and village entrepreneurs. Training covers group decision-making, financial literacy, enterprise management, record keeping, negotiation and digital tools. IPBES rates the distributional equity of medicinal-plant options as a risk (option H04); the women-led model, published selection rules and reporting of who earns are the programme’s response. In the cluster phase, Van Sakhi become the trainers of neighbouring panchayats.

# 7. Digital: VanaGram OS

VanaGram OS is the DEVTech module for biodiversity and agroforestry. A farmer, Van Sakhi or Panchayat Secretary enters land details — district, land category, soil, area and water source — and receives recommendations drawn from government documents, each cited to its clause and date:

- National Agroforestry Policy (2014) and the 2025 model rules for felling trees on agricultural land

- Maharashtra’s tree-felling and transit rules [verify current version]

- NABARD Wadi model and Tribal Development Fund guidelines

- National Medicinal Plants Board and National AYUSH Mission schemes

- VB-G RAM G permissible works; Biological Diversity Act and the 2025 benefit-sharing regulations; Forest Rights Act where relevant

Each recommendation is classified as a direct VB-G RAM G work, a component of an existing work, or a convergence action, and tagged to its IPBES response option. Rules, recommendations and scientific evidence are kept separate, and documents carry their issue date so superseded clauses are flagged. The module also holds the nursery, cultivation, harvest, income and survival records and the PBR — the parcel-level data that later supports nexus modelling. Land records are personal data; the Gram Panchayat is the data fiduciary.

# 8. Institutional roles

| Party | Role |
| --- | --- |
| Gram Panchayat Katlabodi | Land identification and allocation; approvals; convergence with panchayat programmes; constitution or activation of the BMC; Gram Panchayat resolutions |
| Ayurvan Foundation — lead | Technical leadership; species selection; plantation planning; nursery; cultivation protocols; training; processing guidance; market facilitation; biodiversity assessment and PBR support; holder of site assets with the Gram Panchayat |
| UrjaGram Innovations | VanaGram OS and records; monitoring; carbon accounting through the net-zero platform (Project 6); convergence planning; GP-IIP and VGPP preparation; policy and institutional support |
| Self-help groups and Van Sakhi | Nursery work; cultivation; farm records; harvest; primary processing; aggregation; enterprise; market linkage |
| Market partners | Manas Ayurved as anchor buyer; a second buyer to be developed |

A village steering committee — the Gram Panchayat, Ayurvan, UrjaGram and self-help group representatives — reviews land use, plantation progress, participation, production, finances, market linkage, risks and environmental indicators.

# 9. Convergence and funding

| Source | Potential support |
| --- | --- |
| CSR grant (this proposal) | Year-one capital and operating shortfall of the hub site |
| VB-G RAM G | Nursery and plantation labour, land preparation, pits, bunding, soil and moisture conservation, water harvesting and recharge |
| National Medicinal Plants Board; National AYUSH Mission | Cultivation support, planting material, post-harvest infrastructure, training, good practice and certification — at rates applicable under the prevailing scheme |
| NABARD Wadi model and Tribal Development Fund | Orchard-agroforestry for tribal households — relevant to a panchayat that is 52% Scheduled Tribe |
| JICA-supported Capacity Enhancement for Effective Forest Management project (2025–26 to 2031–32) | Pilot site for joint training of forest frontline staff and the Van Sakhi cadre; digital forest-fringe management [verify Maharashtra’s participation] |
| Maharashtra State Biodiversity Board | Grants to the BMC’s Local Biodiversity Fund |
| Agriculture and horticulture schemes; State Rural Livelihoods Mission | Farmer support, enterprise finance and cadre certification |
| Carbon finance | Supplementary, after verification, through the net-zero platform — not assured income |

# 10. Financials

The ten-year model (Project1_Agroforestry_Finances_v2.xlsx) carries over Ayurvan’s cost and revenue estimates unchanged and corrects the calculation structure: revenue now sums species rows only; operation and maintenance is deducted once; and capital cost is included in the cash flow.

| ₹ lakh | Year 1 | Year 2 | Year 3 | Year 5 | Year 10 | 10-year total |
| --- | --- | --- | --- | --- | --- | --- |
| Revenue | 28.2 | 35.7 | 47.6 | 68.6 | 106.7 | 709.9 |
| Operation and maintenance | 44.6 | 45.0 | 45.0 | 45.0 | 47.0 | 459.6 |
| Operating surplus / (shortfall) | (16.4) | (9.3) | 2.6 | 23.6 | 59.7 | 250.3 |
| Capital expenditure | 165.1 | — | — | — | — | 165.1 |
| Cumulative net position | (181.5) | (190.8) | (188.2) | (151.0) | 85.2 | 85.2 |

- Grant. Capital of ₹1.65 crore and the year-one shortfall of ₹16.4 lakh are sought within the CSR grant (budget line D, ₹1.81 crore).

- Operating position. Surplus from year three; ten-year operating surplus of ₹2.50 crore; capital recovered in year nine; ten-year net position ₹0.85 crore, undiscounted.

- Drought test. A drought in year two with illustrative yield losses (30% woody and fruit, 60% fodder, 50% shrubs, 40% nursery, 10% bamboo) reduces ten-year revenue by ₹14.6 lakh and the net position to ₹0.71 crore; payback remains in year nine.

- Dependence on the nursery. Nursery sales are ₹24.75 lakh of ₹28.2 lakh revenue in year one. Their basis is to be documented; demand from the Katol cluster and VB-G RAM G plantation works is the intended market.

- Points to confirm. The year-two shortfall of ₹9.3 lakh falls after the grant period and needs a funding source; the establishment-staff line in capital cost may overlap with year-one operation and maintenance; candidate species are not yet costed.

# 11. Monitoring, carbon and biodiversity

| Indicator | Measure |
| --- | --- |
| Women engaged; self-help group participation | Number; by village |
| Area under cultivation | Hectares, by component |
| Nursery production and sales | Plants; ₹; buyers in the Katol cluster |
| Medicinal and fruit production; offtake | kg or tonnes; ₹; buyers linked |
| Fodder production | Tonnes a year; share of herd requirement met |
| Woody plants planted; survival | Number; % at years 1, 3 and 5 |
| Income generated | ₹ per woman per cycle; share reaching new participants |
| Soil and biodiversity | Selected soil parameters; species diversity; PBR entries |
| Carbon sequestration | tCO₂e by an approved method, estimated and verified volumes kept separate |

Carbon accounting may cover above- and below-ground biomass, soil organic carbon where measurable, survival and growth. Carbon revenue is not treated as project income at this stage: any credit programme requires an eligible boundary, an approved methodology, a baseline, additionality, monitoring, third-party validation and verification, and registration under the selected standard. Accounting runs through the net-zero platform so that Project 1 is counted once, alongside the other projects.

Diversity within productivity. The mix of herbs, aromatic plants, fruit trees, multipurpose trees, bamboo and fodder avoids monoculture and supports habitat, pollinators and soil biology.

# 12. Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Drought recurs | Lower yields and survival | Low-water species; drip; water budget; recharge; stress-tested finances |
| Market price volatility | Lower income | Market first; anchor buyer plus a second buyer |
| Nursery demand below estimate | Operating shortfall | Supply to the Katol cluster and VB-G RAM G works; documented demand before scaling |
| Poor planting material or low tree survival | Ecological and economic loss | Quality nursery; site selection; survival monitoring |
| Pests and disease; crop failure | Production loss | Diversification; good practice; technical advisory |
| Low participation or elite capture | Slow delivery; narrow benefits | Continuous mobilisation; published selection rules; reporting of who earns |
| Regulatory and land issues | Delays | Land-status verification; prior permissions; VanaGram OS rule checks |
| Carbon-credit uncertainty | Revenue uncertainty | Treated as supplementary, not assured |

# 13. Five-year plan

| Period | Focus | Key activities |
| --- | --- | --- |
| Year 1 — establish the hub (CSR grant) | A functioning demonstration and women-led enterprise | Baseline; land and permissions; soil and water assessment; nursery; first crop cycle; woody, fruit and fodder planting with the 2027 monsoon; training; primary processing; first offtake; VanaGram OS live; PBR updated |
| Years 2–3 — serve the cluster | Supply and extension across Katol block | Nursery supplies neighbouring panchayats and VB-G RAM G works; Van Sakhi train cluster cadres; buyer agreements; quality protocols; digital crop records; biodiversity and carbon monitoring |
| Years 4–5 — enterprise and replication | A financially sustainable enterprise and a State-ready model | Scale and diversify species; processing and branding where permissible; certification; carbon and biodiversity accounting; independent assessment; replication package for other talukas |

| Indicator | Year 1 | Years 2–3 | Years 4–5 |
| --- | --- | --- | --- |
| Women engaged | 30–50 | 75–150 | 150+ |
| Nursery | Established | Supplying the cluster | Sustainable enterprise |
| Medicinal cultivation | Pilot | Expanded | Scaled |
| Fodder | Demonstration | Expansion | Village-level coverage |
| Woody plantation | Established | Expanded | Maintained |
| Processing and market | Basic; first offtake | Operational; multiple buyers | Enterprise level; long-term buyers |
| Carbon and biodiversity | Baseline | Monitoring | Verified assessment where applicable |

Targets are indicative and will be finalised after the baseline, land availability and technical feasibility.

# 14. Year-one priority actions

| Phase | Months | Actions |
| --- | --- | --- |
| Preparation | 1–2 | Gram Panchayat approval and site allocation; land-status verification; baseline; soil and water assessment; Van Sakhi and pilot group identified; plantation plan |
| Nursery | 2–6 | Nursery structures and water; procurement of planting material; propagation and hardening; training |
| Site works | 3–6 | Fencing; drip and storage; land preparation; recharge works through VB-G RAM G |
| Planting | 7–8 | Medicinal, fruit, woody, fodder and bamboo planting with the monsoon |
| Enterprise and market | 6–12 | Harvest of early crops; drying, grading, packing; aggregation; buyer samples and quality testing; first offtake |
| Monitoring | 1–12 | VanaGram OS records; survival; production; income; PBR; carbon and biodiversity baseline |

# 15. Conclusion

Project 1 turns suitable village land into a productive community asset, at the moment a drought shows what its absence costs. It combines medicinal plants, agroforestry, fodder, women-led enterprise, market linkage and ecological restoration; it treats biodiversity as infrastructure; and it gives the Katol cluster its nursery and its demonstration. The principle is simple: grow for livelihoods, plant for the future, restore for resilience.

Prepared by Ayurvan Foundation with UrjaGram Innovations Pvt Ltd and Gram Panchayat Katlabodi. Discussion draft — not for external circulation.