CONCEPT NOTE

PROJECT 1: MEDICINAL AGROFORESTRY

Building Livelihoods, Biodiversity and Climate Resilience through Community-Based Medicinal Plant Cultivation

Project Area: Katlabodi, Dhankund and Murli, Katol Block, Nagpur District, Maharashtra
Lead Organisation: Ayurvan Foundation
Community Partner: Gram Panchayat Katlabodi
Technical & Development Partner: UrjaGram Innovations
Primary Beneficiaries: SHG women, small and marginal farmers, livestock-owning households and rural youth
Initial Pilot: Approximately 30–50 SHG women, with potential for subsequent scale-up
Proposed Implementation Period: 5 years, with Year 1 focused on establishment and demonstration

1. Executive Summary

Ayurvan Foundation, in collaboration with Gram Panchayat Katlabodi and UrjaGram Innovations, proposes to implement Project 1 – Medicinal Agroforestry as a core component of the Katlabodi Climate Resilient Village Programme.

The project seeks to establish a community-owned and market-linked medicinal agroforestry system in and around Katlabodi, including the villages of Dhankund and Murli, by combining short-duration medicinal and aromatic crops with long-duration woody species.

The project will create livelihood opportunities for SHG women and local farmers through cultivation, harvesting, primary processing and value addition of medicinal plants, while simultaneously increasing tree cover, biodiversity, soil health, carbon sequestration and climate resilience.

The proposed model will integrate:

Land → Nursery → Medicinal Crops → Agroforestry → SHG Enterprise → Processing → Market Linkage → Income + Carbon + Biodiversity

The project will initially focus on medicinal crops such as Ashwagandha, Kalmegh, Lemongrass, Aloe Vera and Safed Musli, along with woody species such as Amla, Bael, Arjuna, Moringa and Bamboo. Suitable fodder species will also be introduced in convergence with the project's livestock and dairy programme.

A major feature of the project will be the development of an assured market linkage mechanism, with Ayurvan Foundation acting as an anchor organisation and SHGs aggregating produce for processors, Ayurvedic industries and other institutional buyers.

2. Background and Rationale

Rural communities around Katlabodi depend significantly on agriculture, livestock and natural resources for their livelihoods. However, conventional agriculture can be exposed to rainfall variability, water stress, fluctuating input costs and uncertain commodity prices.

At the same time, there is an opportunity to create additional income streams from medicinal and aromatic plants, while restoring ecological functions through agroforestry.

Medicinal plants have several advantages in an appropriate local farming system:

- relatively diversified income opportunities;

- potential for short-duration as well as perennial production;

- suitability for small plots and community demonstration areas;

- opportunities for women-led cultivation and primary processing;

- potential linkages with Ayurvedic and herbal-product value chains;

- integration with tree-based farming;

- improvement in biodiversity; and

- contribution to long-term carbon sequestration.

The proposed project therefore moves beyond conventional plantation activity and establishes an integrated livelihood–ecology model.

3. Project Vision

"Prosperous villages with healthy people, healthy ecosystems and resilient livelihoods."

The project aims to demonstrate that village land can simultaneously generate:

Income + Medicinal Resources + Fodder + Biodiversity + Carbon Benefits + Climate Resilience

4. Project Objectives

4.1 Livelihood Objective

To create additional and sustainable income opportunities for SHG women and farmers through medicinal plant cultivation, processing and market linkage.

4.2 Agroforestry Objective

To establish a diversified agroforestry model combining fast-growing herbaceous medicinal crops with perennial woody species.

4.3 Biodiversity Objective

To increase plant diversity and ecological resilience through the introduction of locally suitable medicinal, fruit-bearing, multipurpose and native tree species.

4.4 Climate Objective

To increase vegetation cover, improve soil health and contribute to long-term carbon sequestration and climate resilience.

4.5 Fodder Security Objective

To establish suitable fodder plantations and integrate them with the livestock development programme to improve year-round fodder availability.

4.6 Women's Empowerment Objective

To place SHG women at the centre of the cultivation, processing and enterprise model, creating opportunities for skill development, income generation and collective entrepreneurship.

4.7 Market Objective

To establish structured market linkages through Manas Ayurved and  Ayurvedic/herbal industries, institutional buyers and other suitable markets.

5. Proposed Project Geography

The project will cover:

- Katlabodi – primary demonstration and community hub

- Dhankund – expansion and farmer/SHG participation

- Murli – expansion and livelihood-linked plantation

Land may be sourced through a combination of:

- Gram Panchayat land, subject to applicable permissions;

- community land, where legally permissible;

- farmer-owned land;

- SHG-managed plots;

- institutional/community demonstration plots; and

- other suitable land made available through lawful arrangements.

The exact land parcels, area and species will be finalised following joint site assessment, land-status verification, soil assessment and water-availability assessment.

6. Land Requirement

The project proposes that the Gram Panchayat Katlabodi identify suitable land in and around Katlabodi for:

- medicinal plant cultivation;

- fodder plantation;

- demonstration agroforestry plots;

- community nursery;

- mother plant/nucleus planting material;

- woody plantation;

- training and demonstration activities; and

- primary processing/value-addition infrastructure, where feasible.

The land requirement should be finalised after the baseline survey.

Indicative Land-use Structure

| Component | Indicative Purpose |
| --- | --- |
| Medicinal crop plots | Short-duration income generation |
| Agroforestry plots | Trees + medicinal crops |
| Fodder plots | Livestock/fodder security |
| Nursery | Planting material production |
| Demonstration plot | Training and technology demonstration |
| Community biodiversity area | Native/multipurpose species |
| Processing area | Drying, grading and packing |

7. Proposed Crop and Species Portfolio

The project will adopt a diversified species portfolio rather than depending on a single crop.

A. Fast-Herbaceous Medicinal/Aromatic Crops

| Species | Indicative Purpose | Expected Benefit |
| --- | --- | --- |
| Ashwagandha | Medicinal root crop | Short-duration income |
| Kalmegh | Medicinal herb | Herbal/Ayurvedic market |
| Lemongrass | Aromatic crop | Essential oil/value addition |
| Aloe Vera | Medicinal/industrial crop | Multiple product applications |
| Safed Musli | High-value medicinal crop | Premium livelihood opportunity |

Selection will depend on soil, rainfall, water availability, agronomic suitability and confirmed market demand.

B. Woody Agroforestry Species

| Species | Primary Function |
| --- | --- |
| Amla | Fruit + livelihood + biodiversity |
| Bael | Fruit + medicinal value |
| Arjuna | Medicinal + ecological |
| Moringa | Nutrition + livelihood |
| Bamboo | Biomass + livelihood + soil protection |

Additional locally appropriate native and multipurpose species may be introduced after technical assessment.

8. Fodder Plantation Component

Medicinal agroforestry will be integrated with fodder security, particularly because Project 3 of the Katlabodi programme focuses on livestock and dairy development.

Suitable perennial and seasonal fodder species may be planted based on:

- local agro-climatic conditions;

- livestock population;

- water availability;

- palatability;

- nutritional value;

- regeneration capacity; and

- local farmer acceptance.

Expected outcomes

- year-round fodder availability;

- reduced dependence on purchased fodder;

- reduced pressure on natural vegetation;

- improved livestock productivity;

- utilisation of suitable community/fallow land;

- integration of fodder cultivation with women's SHG activities.

9. Core Beneficiary Model

Primary Beneficiaries

30–50 SHG women will initially be mobilised as the pilot beneficiary group.

The programme can subsequently be expanded to additional SHGs and farmers.

Secondary Beneficiaries

- local farmers;

- livestock-owning households;

- rural youth;

- nursery workers;

- local labour;

- SHG members;

- village-level entrepreneurs.

10. SHG Women at the Core

The project will adopt a "Women at the Core" enterprise model.

SHG members will participate in:

Nursery → Land Preparation → Cultivation → Good Agricultural Practices → Harvesting → Primary Processing → Drying → Grading → Packing → Aggregation → Market Linkage

Selected SHG members can subsequently be developed as:

- Master Trainers

- Nursery Managers

- Community Resource Persons

- Cultivation Coordinators

- Processing Workers

- Quality-control representatives

- Village-level entrepreneurs

This will enable the project to move from simple plantation activity towards a women-led rural enterprise.

11. Project Implementation Model

The project will follow five major stages.

Stage 1 – Nursery & Planting Material

Establishment of an Ayurvan-supported nursery to produce and supply quality planting material.

Activities include:

- nursery establishment;

- mother stock development;

- seed/planting material procurement;

- nursery training;

- propagation;

- hardening;

- distribution to beneficiaries.

Stage 2 – Cultivation & Good Agricultural Practices

SHGs and farmers will receive technical training covering:

- land preparation;

- planting;

- spacing;

- organic/natural farming practices where feasible;

- irrigation;

- weed management;

- pest and disease management;

- crop-specific harvesting;

- record keeping.

Stage 3 – Harvesting & Primary Processing

The project will develop village-level capacity for:

- harvesting;

- cleaning;

- washing where required;

- drying;

- grading;

- sorting;

- weighing;

- storage; and

- primary packaging.

Stage 4 – Value Addition & Quality Assurance

Depending on the crop and market, value addition may include:

- dried medicinal material;

- graded roots;

- dried leaves;

- herbal raw material;

- essential oil;

- processed plant material; and

- other permissible products.

Appropriate quality standards, traceability and documentation will be introduced.

Stage 5 – Market Linkage & Offtake

Produce will be aggregated through SHGs and linked with suitable:

- Manas Ayurved

- Ayurvedic manufacturers;

- herbal-product companies;

- processors;

- institutional buyers;

- essential-oil processors;

- wholesalers; and

- other verified buyers.

12. Assured Market Linkage Framework

A key principle of the project is:

"Market first, cultivation second."

Before large-scale cultivation of high-value medicinal crops, the project will assess:

- market demand;

- buyer specifications;

- quality requirements;

- expected price;

- quantity requirements;

- harvesting season;

- processing requirements; and

- logistics.

Proposed Market Chain

Ayurvan Foundation
↓
SHGs / Farmer Producer Organisation
↓
Aggregation & Primary Processing
↓
ASU / Herbal Industry / Institutional Buyer

Where possible, a second buyer/market channel will be developed to reduce dependence on a single purchaser.

13. Institutional Roles

A. Gram Panchayat Katlabodi

The Gram Panchayat will provide:

- facilitation of land identification;

- community mobilisation;

- local approvals/support;

- convergence with Panchayat programmes;

- coordination with village institutions;

- facilitation of Gram Sabha processes;

- support for community infrastructure.

B. Ayurvan Foundation – Lead Organisation

Ayurvan Foundation will provide:

- technical leadership;

- species selection;

- plantation planning;

- nursery support;

- cultivation protocols;

- capacity building;

- SHG training;

- processing guidance;

- market facilitation;

- documentation;

- monitoring;

- biodiversity and carbon assessment;

- coordination with relevant institutions.

C. UrjaGram Innovations – Technical/Development Partner

UrjaGram Innovations will support:

- project development;

- digital MIS;

- AI/digital applications where relevant;

- project monitoring;

- data management;

- convergence planning;

- policy and institutional support;

- carbon and climate integration.

D. SHGs

SHGs will be responsible for:

- participation in cultivation;

- nursery activities;

- maintaining farm records;

- harvesting;

- primary processing;

- aggregation;

- enterprise activities; and

- participation in market linkage.

14. Convergence and Funding Opportunities

The project will explore convergence with relevant Government programmes, subject to scheme guidelines, eligibility and approval.

National Medicinal Plants Board / National AYUSH Mission

Potential areas of convergence may include:

- cultivation support;

- nursery/planting material;

- post-harvest infrastructure;

- capacity building;

- Good Agricultural Practices;

- certification-related support.

The attached project concept identifies indicative cultivation support levels of 30% / 50% / 75%, but the applicable assistance will be determined according to the prevailing scheme and eligibility conditions at the time of application.

MGNREGS

Potential convergence areas include eligible activities such as:

- land preparation;

- water harvesting;

- bunding;

- pit digging;

- soil and moisture conservation;

- plantation-related labour activities, where permissible.

Other Potential Sources

The project may also explore:

- CSR funding;

- State Government schemes;

- District-level convergence;

- National AYUSH Mission;

- agriculture/horticulture programmes;

- tribal/rural livelihood programmes, where applicable;

- SHGs development programmes;

- community contributions.

15. Five-Year Implementation Strategy

Year 1 – Establishment & Demonstration

Key activities:

- baseline survey;

- land identification;

- land-status/permission verification;

- soil and water assessment;

- SHG mobilisation;

- nursery establishment;

- species selection;

- first medicinal crop cycle;

- agroforestry plantation;

- fodder demonstration;

- training;

- primary processing;

- initial market linkage;

- establishment of MIS.

Year-1 Target

Establish a functioning community medicinal agroforestry demonstration and SHG enterprise model.

Year 2 – Expansion

- expand cultivation area;

- increase SHG participation;

- strengthen nursery;

- introduce additional farmers;

- strengthen SHGs aggregation;

- establish buyer agreements;

- improve processing;

- introduce digital crop records;

- initiate biodiversity and carbon monitoring.

Year 3 – Enterprise Development

- scale medicinal crop production;

- strengthen value addition;

- improve packaging;

- establish quality protocols;

- develop branded/market-ready products where legally permissible;

- strengthen institutional buyers;

- increase fodder production;

- establish community-level business systems.

Year 4 – Scale & Diversification

- expand to additional villages/farmers;

- diversify species;

- strengthen SHGs operations;

- improve processing infrastructure;

- explore certification;

- develop carbon/biodiversity accounting;

- strengthen long-term buyer relationships.

Year 5 – Consolidation & Replication

- establish financially sustainable enterprise;

- document impact;

- undertake third-party/independent assessment where appropriate;

- develop replication model;

- expand across additional villages;

- integrate with wider Katlabodi Climate Resilient Village Programme.

16. Indicative Activity Calendar

| Activity | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- |
| Baseline assessment | ✓ |  |  |  |  |
| Land identification | ✓ | ✓ |  |  |  |
| Nursery establishment | ✓ | ✓ | ✓ | ✓ | ✓ |
| SHG mobilisation | ✓ | ✓ | ✓ | ✓ | ✓ |
| Medicinal crop cultivation | ✓ | ✓ | ✓ | ✓ | ✓ |
| Woody plantation | ✓ | ✓ | ✓ | ✓ | ✓ |
| Fodder plantation | ✓ | ✓ | ✓ | ✓ | ✓ |
| Training | ✓ | ✓ | ✓ | ✓ | ✓ |
| Primary processing | ✓ | ✓ | ✓ | ✓ | ✓ |
| SHG development | ✓ | ✓ | ✓ | ✓ | ✓ |
| Market linkage | ✓ | ✓ | ✓ | ✓ | ✓ |
| Carbon monitoring | ✓ | ✓ | ✓ | ✓ | ✓ |
| Scale-up |  | ✓ | ✓ | ✓ | ✓ |

17. Monitoring, Reporting and Verification – MRV

A digital monitoring system will be established to track physical, social, economic and ecological performance.

Key Indicators

| Indicator | Measurement |
| --- | --- |
| Women engaged | Number of SHG members |
| Area under cultivation | Acres/hectares |
| Medicinal crop production | kg/MT |
| Fodder production | MT/year |
| Woody plants planted | Number |
| Woody survival rate | % |
| Nursery production | Number of plants |
| Training delivered | Number of sessions/persons |
| Income generated | ₹/woman/cycle |
| Offtake volume | kg/MT |
| Buyers linked | Number |
| SHGs participation | Members |
| Soil improvement | Selected soil parameters |
| Biodiversity | Species/plant diversity |
| Carbon sequestration | tCO₂e, based on appropriate methodology |

18. Carbon Sequestration and Climate Benefits

The project will contribute to climate action primarily through the establishment and survival of woody biomass, soil-health improvement and increased vegetation cover.

The project will establish a baseline and subsequently estimate carbon sequestration using appropriate and defensible methodologies.

Carbon accounting may cover:

- above-ground biomass;

- below-ground biomass;

- soil organic carbon, where measurable;

- plantation survival;

- incremental tree growth.

Importantly, carbon-credit revenue should not be treated as guaranteed project income at the concept stage. Any future carbon-credit programme will require:

- eligible project boundary;

- approved methodology;

- baseline determination;

- additionality assessment;

- monitoring;

- third-party validation/verification, as applicable; and

- registration/issuance under the selected carbon standard.

19. Biodiversity Benefits

The project will deliberately avoid creating a monoculture-based plantation model.

Instead, it will promote:

"Diversity within Productivity."

The integration of medicinal herbs, aromatic plants, fruit trees, multipurpose trees, bamboo and fodder species can create a more diverse production landscape.

Expected biodiversity benefits include:

- increased plant diversity;

- habitat improvement;

- pollinator support;

- improved soil biological activity;

- reduced dependence on a single crop;

- improved ecological resilience.

20. Gender and Social Inclusion

Women will be central to the project rather than being treated only as beneficiaries.

The project will create opportunities for women to participate across the value chain:

Production → Processing → Quality → Aggregation → Enterprise → Market

Special emphasis will be given to:

- SHG-based decision making;

- financial literacy;

- enterprise management;

- record keeping;

- leadership;

- market negotiation;

- digital tools;

- development of women master trainers.

21. Risk Assessment and Mitigation

| Risk | Potential Impact | Mitigation |
| --- | --- | --- |
| Market price volatility | Lower income | Advance buyer identification and diversified markets |
| Crop failure | Production loss | Crop diversification and technical advisory |
| Water shortage | Reduced productivity | Water harvesting and drought-tolerant species |
| Poor planting material | Low survival/yield | Quality nursery and technical supervision |
| Low survival of trees | Ecological/economic loss | Site selection, maintenance and survival monitoring |
| Lack of market | Unsold produce | Manas Ayurved + anchor buyer + second buyer |
| Pest/disease | Crop loss | Good Agricultural Practices and monitoring |
| Low SHG participation | Slow implementation | Continuous mobilisation and incentives |
| Regulatory issues | Project delays | Prior permissions and compliance |
| Carbon-credit uncertainty | Revenue uncertainty | Treat carbon revenue as supplementary, not assured |

22. Sustainability Strategy

The project will be designed so that the programme gradually moves from grant-supported establishment to community-owned enterprise.

The sustainability model will comprise:

Ecological Sustainability

Trees + medicinal plants + fodder + biodiversity

Economic Sustainability

Crop income + processing + market linkage + enterprise margins

Institutional Sustainability

Gram Panchayat + SHGs  + Ayurvan + technical partners+ Manas Ayurved

Financial Sustainability

Product revenue + convergence funding + CSR support + potential carbon finance

Social Sustainability

Women-led enterprise + local employment + community ownership

23. Expected Five-Year Outcomes

By the end of five years, the project aims to establish:

- a functioning community medicinal agroforestry model;

- a sustainable SHG-led cultivation system;

- a community nursery;

- medicinal crop production across identified suitable areas;

- integrated fodder plantations;

- woody agroforestry plantations;

- trained SHG women and village resource persons;

- primary processing capacity;

- collective aggregation;

- institutional buyer linkages;

- digital MIS and traceability;

- measurable biodiversity improvement;

- measurable tree survival and biomass growth;

- a framework for carbon accounting;

- increased livelihood opportunities; and

- a replicable model for other villages.

24. Key Performance Indicators – Five-Year Framework

| KPI | Year 1 | Year 2–3 | Year 4–5 |
| --- | --- | --- | --- |
| SHG women engaged | 30–50 | 75–150 | 150+ |
| Community nursery | Establish | Expand | Sustainable |
| Medicinal cultivation | Pilot | Expand | Scale |
| Fodder plantation | Demonstration | Expansion | Village-level coverage |
| Woody plantation | Establish | Expand | Mature/maintained |
| Processing | Basic | Strengthen | Enterprise level |
| Market linkage | Initiate | Operationalise | Scale |
| Buyers | Initial | Multiple | Long-term |
| Carbon MRV | Baseline | Monitoring | Verified assessment, where applicable |

Targets are indicative and should be finalised following baseline assessment, land availability and technical feasibility.

25. Proposed Governance Structure

Village Steering Committee

Gram Panchayat Katlabodi
↓
Ayurvan Foundation – Project Lead
↓
UrjaGram Innovations – Technical/Digital Partner
↓
SHG Representatives
↓
Farmers & Community

The Steering Committee will periodically review:

- land use;

- plantation progress;

- SHG participation;

- production;

- financial performance;

- market linkage;

- risks;

- environmental indicators.

26. Linkages with Other Katlabodi Climate Resilient Village Projects

Medicinal Agroforestry will not operate as a standalone intervention.

Project 1 → Medicinal Agroforestry

Income + Biodiversity

↓

Project 2 → Village Water Security

Water availability for cultivation and plantation

↓

Project 3 → Livestock & Dairy

Fodder security + livestock livelihood

↓

Project 4 → Clean Energy & Net-Zero

Biogas + renewable energy + carbon accounting

This creates an integrated village development model:

Healthy Forests → Secure Water → Prosperous Farmers → Strong Livestock → Clean Energy

27. Proposed Year-1 Priority Actions

The first year should focus on creating a visible and functioning demonstration model.

Phase I – Preparation

- Gram Panchayat approval;

- land identification;

- baseline survey;

- soil/water assessment;

- SHG identification;

- detailed plantation plan.

Phase II – Nursery

- nursery establishment;

- procurement of planting material;

- propagation;

- training.

Phase III – Plantation

- land preparation;

- medicinal crop planting;

- woody plantation;

- fodder plantation.

Phase IV – Enterprise

- harvesting;

- drying;

- grading;

- packaging;

- aggregation.

Phase V – Market

- buyer identification;

- sample development;

- quality testing where required;

- SHG aggregation;

- initial offtake.

Phase VI – Monitoring

- digital MIS;

- survival monitoring;

- production records;

- income tracking;

- carbon/biodiversity baseline.

28. Indicative Theory of Change

LAND & NATURAL RESOURCES
↓
Suitable community/farmer land
↓
QUALITY PLANTING MATERIAL
↓
Medicinal + aromatic + woody + fodder species
↓
SHG CAPACITY BUILDING
↓
Good Agricultural Practices
↓
CULTIVATION & AGROFORESTRY
↓
Harvest + Processing + Value Addition
↓
COLLECTIVE AGGREGATION
↓
Assured Market Linkages
↓
HIGHER & DIVERSIFIED RURAL INCOME
↓
BIODIVERSITY + FODDER SECURITY + CARBON SEQUESTRATION
↓

CLIMATE-RESILIENT AND PROSPEROUS VILLAGE

29. Conclusion

Project 1 – Medicinal Agroforestry is proposed as a flagship livelihood and ecological restoration intervention under the Katlabodi Climate Resilient Village Programme.

The project is designed around a simple principle:

"Grow for livelihoods, plant for the future, restore for resilience."

By combining medicinal plants, agroforestry, fodder, women-led enterprise, market linkages and ecological restoration, the project can transform suitable village land into a productive community asset.

The proposed partnership between Gram Panchayat Katlabodi, Ayurvan Foundation and UrjaGram Innovations provides an institutional framework for combining community ownership, technical expertise, digital systems and market-oriented implementation.

The project will therefore seek to create not merely a plantation, but a replicable village-level medicinal agroforestry enterprise model that delivers measurable benefits in terms of:

Livelihoods • Women's Empowerment • Biodiversity • Fodder Security • Carbon Sequestration • Climate Resilience • Rural Enterprise