PROPOSAL FOR CORPORATE SOCIAL RESPONSIBILITY FUNDING

Katlabodi Integrated Village Development Project

Drought to resilience — a Gram Panchayat hub for Katol block and a model for Maharashtra

| Submitted by | Ayurvan Foundation — registered public trust and society; on-ground implementation lead and grant recipient |
| --- | --- |
| Submitted to | Mr Manish Satyanarayan Nuwal Managing Director & CEO Solar Industries India Limited “Solar” House 14, Kachimet, Amravati Road, Nagpur 440023 (+91) 712-6634555, (+91) 712-6634550 · solar@solargroup.com |
| Implementation partners | Gram Panchayat Katlabodi — land, approvals, community mobilisation and data custodianship UrjaGram Innovations Pvt Ltd — framework, technology platform, project development, monitoring and policy partner |
| Location | Gram Panchayat Katlabodi — villages of Katlabodi, Murli and Dhankundav; Katol Block, Nagpur District, Maharashtra |
| Programme period | Twelve months from sanction. Target start: December 2026, to use the 2026–27 dry-season works window |
| Financial ask | ₹2.06 crore costed to date — human capital ₹24.30 lakh and Project 1 hub site ₹1.81 crore. Platform and programme-management lines are being finalised (section 15) |
| Date | September 2026 |

Note on figures. Population, household, land-use and literacy data are from the Census 2011 village directory. Livestock figures are from the Gram Panchayat’s animal register. Drought figures are from Government of Maharashtra announcements as reported in The Times of India, September 2026. Scientific findings are cited to the IPBES Nexus Assessment (2024). Items marked [verify] will be confirmed before submission or during the baseline phase.

# 1. Executive summary

The drought is the reason to start now. In September 2026 the Government of Maharashtra declared drought in 265 of its 358 talukas — 74 per cent of the State — after rainfall fell below 75 per cent of normal with dry spells of 21 days or more. Vidarbha is the worst-affected region, and Nagpur district is among the six districts with the most talukas declared. Across the State, kharif crops have failed, rabi sowing is in doubt, water arrives by tanker, cattle are being sold at a fraction of their value for want of fodder, and families are leaving for work months earlier than usual.

Katlabodi carries every part of that risk. Gram Panchayat Katlabodi is a forest-fringe tribal settlement of 717 people in 160 households, across three villages in Katol block. Fifty-two per cent of its residents belong to Scheduled Tribes — four times the share of the block — yet the block carries no tribal classification, so most tribal-area instruments do not reach it. Three-quarters of its sown area depends on groundwater; its herd of 906 animals needs roughly 2,000 tonnes of fodder a year against a few hundred tonnes of local residue; and its 416 hectares of forest absorb the grazing and fuelwood pressure of every failed season. Water, fodder, income and health fail together.

Relief alone will not change that. Drought relief arrives sector by sector, from the top, in short cycles, with no shared platform to plan, deliver and measure across them. The IPBES Nexus Assessment (2024) reaches the same conclusion at global scale: biodiversity, water, food, health and climate change are interlinked, and responses designed in sectoral silos produce trade-offs and unintended consequences.

The answer is the UrjaGram Sustainable Development Framework (USDF). USDF converges adaptation and mitigation into one plan for a Gram Panchayat, and stands on two pillars: DEVTech, the digital pillar that plans, delivers and measures; and local capacity — women’s cadres, students and interns — who run it. Six village projects have been designed for Katlabodi: biodiversity and medicinal agroforestry; water security; livestock and dairy; clean energy; community health and nutrition; and a net-zero and carbon revenue platform that measures and monetises the result of the other five. A tripartite agreement between Ayurvan Foundation, the Gram Panchayat and UrjaGram Innovations was signed on 13 July 2026 for five years.

## What this proposal asks for

Corporate social responsibility funding for twelve months, to do four things:

- Build local capacity. Train fifty people — twenty women from self-help groups as five project-specific cadres, twenty school students, and ten engineering and management interns — and employ one tutor and one local project manager.

- Deploy the digital pillar. Customise DEVTech for Katlabodi, including VanaGram OS, and release it as open-source software that any Gram Panchayat may use free of charge.

- Establish the hub site. Build the Project 1 nursery and medicinal agroforestry demonstration site, which supplies planting material to the Katol cluster and demonstrates drought-resilient land use.

- Produce the plan and the evidence. Establish baselines and produce Katlabodi’s Gram Panchayat Integrated Investment Plan (GP-IIP) — prepared as the climate-integrated Viksit Gram Panchayat Plan required under VB-G RAM G — with six project documents to bankable standard.

## From hub to State

Katlabodi is the hub. From year two the model extends across the Katol block cluster, and within five years it offers a proven, costed and replicable model, ready for adoption across Maharashtra’s 358 talukas through the State’s own Gram Panchayat planning process. Maharashtra’s 1972 drought produced the Employment Guarantee Scheme; the 2026 drought can produce a working model of village climate resilience.

## Why corporate social responsibility funding

Corporate social responsibility funding cannot, and is not asked to, deliver the ten-year outcomes of these projects; those will be financed through VB-G RAM G and other government schemes, banks, and climate and blended finance. What the grant can do — and what nothing else will pay for — is build the local capacity, the platform, the hub site and the project preparation that make those larger flows possible. The grant does not buy the outcome; it buys the investability of the outcome, and that is fully attributable to the grant and achieved within the grant period.

## What already exists

- A signed tripartite agreement with the elected Gram Panchayat, dated 13 July 2026, valid for five years.

- Ayurvan Foundation’s presence in the village, with community trust and market linkages for medicinal produce.

- Four DEVTech components under development, three of them in production, funded by UrjaGram and built by interns from VNIT Nagpur, NIT Jalandhar and NIT Kurukshetra.

- An evidence base: an analysis of the livestock register, a sourced socio-economic baseline, a block-level pre-feasibility evaluation of dairy, biogas and biofertiliser infrastructure, and a Project 1 financial model.

- Project briefs with activities, convergence routes, indicators and risks; and an academic engagement with VNIT Nagpur.

# 2. Why now: the 2026 drought

## 2.1 What the drought has done

| Measure | Position in September 2026 |
| --- | --- |
| Talukas declared in drought | 265 of 358 (74%), across 34 of 36 districts — wider than any declaration of the past decade |
| Trigger met | Trigger 1 of the Centre’s Drought Management Code 2016: rainfall below 75% of normal and a dry spell of 21 days. Later triggers assess sowing, groundwater, soil moisture and vegetation |
| Rainfall | State deficit of 17–18%; 27 of 36 districts below normal (1 June–21 September) |
| Worst-affected region | Vidarbha, 95 talukas. Nagpur district among the six worst-affected, with 14 talukas declared [verify inclusion of Katol in the Government Resolution] |
| Relief announced | Twelve measures, including crop-loan restructuring, drinking-water tankers, food grain and fodder for livestock, and additional water-conservation works. Crop compensation after the October damage assessments |

Reports from affected districts describe the pattern that Katlabodi is exposed to: cotton and soybean failing at a fraction of a normal yield, orchards drying, tankers as the only drinking-water source, fodder unaffordable and cattle sold cheaply, unpaid input bills, and migration starting months early.

## 2.2 What it means for Katlabodi

- Water. 74 per cent of the sown area is irrigated, almost certainly from groundwater. A rainfall shortfall becomes an aquifer shortfall, and recharge turns episodic against continuous extraction.

- Fodder and livestock. The herd’s fodder need exceeds local supply several times over in a normal year. In a drought year the gap widens exactly when the herd — the panchayat’s largest asset — most needs it.

- Forest. The 416 hectares of forest take the grazing and fuelwood pressure of a failed season, eroding the ecosystem services on which fodder, water and livelihoods depend.

- Health. Heat, untreated drinking water and poor-year nutrition fall on the same households, and on women and children first.

## 2.3 The window

The dry season is when resilience is built. Starting in December 2026 allows the programme to use the 2026–27 dry season before the next monsoon; a later start loses a full year.

| When | Action | If delayed |
| --- | --- | --- |
| Dec 2026 – Feb 2027 | Baselines recorded while drought stress is measurable; water mapping and budgeting; drought contingency plan for fodder and water; cadre selection | The stress state goes unrecorded, and the next shortfall meets the same unprepared system |
| Jan – May 2027 | Recharge and repair works through VB-G RAM G convergence; hub nursery raised; site preparation | Structures miss the 2027 monsoon; recharge is lost for a year |
| Jun – Jul 2027 | Planting of fodder, medicinal and woody species at the hub site | Planting slips to 2028; income and fodder benefits slip with it |

## 2.4 Why single-sector relief is not enough

| How schemes usually arrive | How this programme responds |
| --- | --- |
| Fragmented — energy, water, health and agriculture rarely addressed together | Six linked projects in one GP-IIP; one household record across all of them |
| Top-down — rarely co-designed with the community | Gram Panchayat resolutions; selection rules adopted before names are proposed; a local cadre that delivers |
| Short-term — one-to-three-year cycles for multi-decade problems | A one-year grant that produces a ten-year investment plan and the finance routes to deliver it |
| Not scalable — each village starts from scratch | Open-source platform, trainer cascade and a GP-IIP template for the Katol cluster and beyond |
| No platform — nothing to coordinate, monitor and learn across villages | DEVTech, with measurement conservative by construction |

IPBES finds that response options implemented together or in sequence enhance their benefits and can reduce costs compared with siloed policies (IPBES SPM, C10, p. 40).

# 3. Katlabodi: the place and the evidence

The programme plans, delivers and reports at panchayat level. The panchayat covers six revenue villages, of which three are inhabited and three are Rithi, or uninhabited. All three inhabited villages are served directly.

## 3.1 Population and social composition

| Village | Population | Households | ST share | Area (ha) | Note |
| --- | --- | --- | --- | --- | --- |
| Katlabodi | 443 | 103 | 46.1% | 173.35 | Largest settlement; primary school |
| Murli | 186 | 40 | 71.0% | 263.34 | Highest ST share; >5 km off bus route |
| Dhankundav | 88 | 17 | 43.2% | 234.47 | Pre-primary only; no primary school |
| Gram Panchayat | 717 | 160 | 52.2% | 671.16 | Three inhabited villages |

The Scheduled Tribe share of 52.2 per cent compares with 13.1 per cent for Katol taluka and 9.4 per cent for Nagpur district — a tribal pocket inside a block that carries no tribal classification.

## 3.2 Land and the production base

| Land use | Hectares | Share | Implication |
| --- | --- | --- | --- |
| Forest | 416.28 | 62.0% | Herd grazes here; access is a livelihood question |
| Net sown area | 190.10 | 28.3% | 1.19 ha per household — small and marginal |
| — of which irrigated | 141.25 | 74.3% of sown | Very high for Vidarbha; almost certainly groundwater |
| Permanent pasture | 31.62 | 4.7% | Nowhere near sufficient for 906 animals |
| Total | 671.16 | 100% |  |

## 3.3 Livestock — the largest asset

The panchayat’s register records 906 animals held by 82 owners. The ten largest owners hold 42 per cent of the herd and eight extended-family groups hold 73 per cent; Katlabodi village holds 61 per cent, Murli 30 per cent and Dhankundav the remainder. At six kilograms of dry matter per animal per day, the herd needs about 2,000 tonnes of fodder a year against a few hundred tonnes of crop residue. Fodder is the binding constraint.

Design consequence. Large herd owners act as anchors that make the milk collection point and cattle facility viable. Every other household, including those with no animals today, is linked to the same infrastructure — fodder bank, cattle facility, collection point, artificial insemination and animal-health support — on equal terms. Selection criteria are adopted in the Gram Panchayat before individuals are proposed, and the share of incremental income reaching the bottom half of owners is reported alongside total volume.

## 3.4 Services and access

| Service | Position today | Consequence |
| --- | --- | --- |
| Secondary schooling | None in the panchayat; nearest at Katol or Yenwa, 30 km away | Drives the 18-point female literacy gap; shapes the student component |
| Drinking water | Untreated tap, hand pumps, uncovered wells in all three villages | A Jal Jeevan Mission gap; acute in drought |
| Banking | None; nearest more than 10 km away | Self-help group dependence on informal credit |
| Power | About 12 hours a day | Adequate domestically; marginal for cold chain |
| Transport | Murli and Dhankundav more than 5 km off the bus network | Katlabodi village holds 62% of the population and 64% of households; facilities must be sited for all three |
| Literacy | 77.4% overall; male 86.0%, female 67.7% | The clearest human-capital target |

# 4. USDF: one framework, two pillars

USDF is UrjaGram’s framework for climate adaptation, mitigation and sustainable development at the scale of a Gram Panchayat. It converges the sectors that fail together into one plan, and rests on two pillars:

- The digital pillar — DEVTech. A village-scale platform that plans, delivers and measures: household and asset registers, sector modules, a digital twin of the panchayat, and a measurement layer that keeps estimated, verified and issued results separate (section 5).

- The local-capacity pillar. Women’s cadres, students and interns who operate the platform and deliver the projects, so that capability stays in the village when the grant ends (section 6).

The output that joins them is the Gram Panchayat Integrated Investment Plan (GP-IIP): a ten-year, projectised and financed plan, prepared in year one and delivered from year two (section 7).

## 4.1 The six village projects

The projects are interdependent by design. Water security makes land reliably cultivable and so enables agroforestry and fodder; the livestock facility supplies feedstock to the biogas plant; the digester returns slurry to the agroforestry plots; and local food, milk and clean cooking supply the nutrition and household-air components of the health project. Projects 1 to 5 change what happens in the panchayat; Project 6 measures that change to a standard that can be verified and sold. Each draws on response options assessed by IPBES — among them agroforestry (C11), groundwater governance and community water management (W09, W15), One Health (H14), sustainable bioeconomy through biogas (C07) and sustainable use of medicinal plants (H04). Activities are indicative and will be finalised with the Gram Panchayat.

| Project | Ten-year outcome | Year-one contribution |
| --- | --- | --- |
| 1. Biodiversity and medicinal agroforestry (Annex D) | Degraded and marginal land carries a permanent woody and medicinal asset; women’s self-help groups capture processing margin; biodiversity is managed as infrastructure that provides ecosystem services | Hub nursery and demonstration site built; species and land assessment; People’s Biodiversity Register updated; Van Sakhi cadre trained; producer organisation constituted or linked |
| 2. Village water security | Extraction and recharge in measured balance; reliable cropping across two seasons | Water mapping and budget; drought contingency plan; hydrogeological read; priority recharge and repair works through VB-G RAM G; drip demonstration; monitoring baseline |
| 3. Livestock, dairy and AI-enabled breeding | An organised, women-operated, lower-emission value chain with benefits deliberately widened | Register re-verified; fodder bank and drought fodder plan; cattle facility and milk collection point; Pashu Sakhi cadre; livestock module with Marathi voice advisory |
| 4. Clean energy | Cooking and institutional energy from local clean sources; less pressure on the forest | First solar installations on public institutions; biogas plant designed and sited; household transition to clean cooking begins |
| 5. Community health and nutrition | Households healthy by practice and choice, with diverse local diets and access to entitled services | Nutrition baseline; local diets and indigenous practice documented; heat-action protocol; entitlement and facility gap analysis to the district; Poshan Sakhi cadre; nutrition gardens |
| 6. Net-zero platform and carbon revenue | Any Gram Panchayat can measure its carbon balance to a verifiable standard and, pooled with others, earn carbon revenue | Configurable net-zero module; Katlabodi baseline carbon account; methodology gap analysis; carbon-rights ownership resolved; block aggregation designed |

## 4.2 Project 1 — the hub site

Project 1 is the physical anchor of the hub. A one-hectare nursery and about four hectares of medicinal, fruit, woody and fodder plantation, with boundary bamboo, demonstrate drought-resilient land use and supply planting material to the Katol cluster and to VB-G RAM G plantation works. The species portfolio combines woody medicinal species (amla, bael, hirda, moringa), fruit species (mango, sitaphal, mulberry, lemon, jamun, ber, karvanda), medicinal shrubs (ashwagandha, kalmegh, gulab, aloe vera, brahmi) and fodder grass, with lemongrass, safed musli and arjuna as candidates subject to market and site assessment. Produce is sold “market first, cultivation second”, with an anchor buyer and a second buyer. Full design and a ten-year financial model are at Annex D.

The corrected model shows an operating surplus from year three, a ten-year operating surplus of ₹2.50 crore before capital cost, and recovery of the ₹1.65 crore capital cost in year nine. A drought in year two reduces ten-year revenue by about ₹15 lakh without changing the payback year.

## 4.3 Project 6 is a platform

Project 6 differs in kind from the other five. It builds a configurable instrument that any panchayat can use, released under the same open-source licence as the rest of the platform; Katlabodi is its first configuration. The module keeps a carbon account (enteric fermentation, manure, fertiliser, pumping, cooking fuel and transport, set against removals and avoided emissions); lets each panchayat set its own boundary, data sources, factors and target year; captures activity data through the cadres rather than a separate survey; accounts for the existing forest as a carbon stock; pools panchayats so that verification costs are shared; generates registry-agnostic documentation; and records benefit-sharing transparently. Estimated, verified and issued volumes are never merged.

Two structural conditions govern it. The approved offset methodologies under India’s Carbon Credit Trading Scheme do not yet cover village-scale biogas, inland agroforestry, soil carbon or livestock methane, so the near-term route is the voluntary standards [verify against current Bureau of Energy Efficiency documentation]. And verification costs cannot be carried by one panchayat, so aggregation across the Katol cluster is the condition of viability. Carbon revenue is a year-three-to-five outcome and is not represented as a year-one result.

# 5. Pillar one: DEVTech

DEVTech is a village-scale delivery and measurement platform developed and funded by UrjaGram. Four components are under development, three of them in production, and all are contributed in kind. The grant funds customisation and deployment for Katlabodi and release as a public asset — not the building of a platform. The platform responds to two gaps named by IPBES: the lack of indicators and data to monitor nexus interlinkages at the local scale at which they are managed (SPM Box SPM.2, p. 42), and the need to use artificial intelligence, digital twins and integrated modelling to quantify those interlinkages (SPM Appendix 3, p. 53).

## 5.1 What exists today

| Component | Function |
| --- | --- |
| Energy platform — VET-OS | Rooftop solar assessment structured on the PM Surya Ghar ten-stage journey, with drop-off tracking and escalation; clean-cooking transition calculator; field data-collection workflow |
| Livestock and biogas portal | Household and per-animal registration; community biogas viability engine with weather-driven heat-stress indexing; dung and milk procurement desk with quality grading and payment; veterinary referral queue |
| Water and farmer platform — AquaGram OS | Multilingual mobile application with field records, input health scoring, advisory and a water-credits ledger that separates estimated from settled values |
| Biodiversity and agroforestry platform — VanaGram OS | Preliminary design by VNIT Nagpur students, financed by UrjaGram until funding is received |

## 5.2 VanaGram OS

A farmer, Van Sakhi or Panchayat Secretary enters land details — district, land category, soil, area and water source — and VanaGram OS returns recommendations drawn from government documents, each cited to its clause and date: the National Agroforestry Policy, the 2025 model rules for felling trees on agricultural land, Maharashtra’s felling and transit rules, NABARD Wadi and Tribal Development Fund guidelines, National Medicinal Plants Board and National AYUSH Mission schemes, VB-G RAM G works, and the Biological Diversity Act. Each recommendation is classified as a direct VB-G RAM G work, a component of an existing work, or a convergence action, and tagged to its IPBES response option. Rules, recommendations and scientific evidence are kept separate. Over time, each parcel’s inputs and results become the local data that quantifies nexus linkages — the foundation for IPBES-based modelling.

## 5.3 What the grant funds

| Work package | Scope |
| --- | --- |
| B1 | Katlabodi instance covering all three villages, and a household identity spine so that one household is one record across every module |
| B2 | VanaGram OS — completion, including the document-grounded advisory |
| B3 | Water module rebuilt for the region, in Marathi and against the applicable scheme environment |
| B4 | Health and nutrition module, co-designed with its users |
| B5 | Configurable net-zero and carbon revenue module (Project 6) |
| B6 | Data protection and security layer, including Marathi consent capture, role-based access, retention rules and breach response |
| B7–B8 | Open-source release; hosting, devices and field connectivity for year one |

Domain ownership. Interns build; they do not specify. Species selection, collection practice, grading standards and model constants are specified and signed off by the named domain owner — Ayurvan for conservation and ecology, UrjaGram for its specialist domains — before implementation.

## 5.4 Open source, free panchayat use and closed data

- The platform is released under the GNU Affero General Public License version 3, with the public repository published by month nine — after the data protection work is complete.

- The Gram Panchayat, and any other panchayat, uses the platform free of charge.

- Open source applies to the code, not to village data. The Gram Panchayat is the data fiduciary, by resolution, with Ayurvan and UrjaGram as processors under a written agreement.

- Disclosure. UrjaGram Innovations is a for-profit company. Its prior development is contributed in kind; code funded by this grant is released openly; and UrjaGram earns from project development and services, not from licence fees charged to panchayats.

# 6. Pillar two: local capacity

This is the core of what the grant pays for. Fifty people are trained and two employed, in a mentorship ladder: engineering interns bring technical and data skills; management interns bring business modelling and finance from month seven; students collect field data and learn by doing; and women’s cadres, trained as project managers, carry delivery across all three villages. The World Bank’s World Development Report 2026 finds that the binding constraint on artificial intelligence in developing economies is the capacity to adopt it; this programme tests whether a Gram Panchayat can run the adopt-and-adapt sequence itself.

## 6.1 Women’s cadres — twenty

Twenty women from existing self-help groups form five cadres of four, serving Projects 1 to 5; Project 6 draws its data from the others. The structure builds on the government’s community-cadre architecture, so that government training carries the base layer and the grant funds the project-specific layer. These are the climate-resilience cadres the VB-G RAM G planning process needs.

| Cadre | Project | Function | Platform module |
| --- | --- | --- | --- |
| Van Sakhi | Biodiversity and agroforestry | Nursery, cultivation, collection practice, grading; People’s Biodiversity Register; forest and biodiversity mapping | VanaGram OS — year one |
| Jal Sakhi | Water security | Water mapping, budgeting, structure monitoring, micro-irrigation, drought contingency | Rebuilt for the region — year one |
| Pashu Sakhi | Livestock and dairy | Registration, health observation, breeding support, milk collection, fodder | In production |
| Urja Sakhi | Clean energy | Household energy assessment, solar facilitation, clean cooking, biogas connections | In production |
| Poshan Sakhi | Health and nutrition | Dietary assessment, indigenous practice, nutrition gardens, heat protocol, entitlements and referral | Year one |

- Distribution. Two per cadre in Katlabodi and one each in Murli and Dhankundav — deliberately over-weighting the smaller villages.

- Recognised equivalents. Each cadre is mapped to its national or state counterpart [verify against state rural livelihoods mission nomenclature].

- Selection. Through the Gram Panchayat against published criteria agreed before names are proposed.

## 6.2 Students — twenty, and one tutor

Twenty students relate textbook mathematics and science to live project work using the platform. A tutor teaches from the syllabus and protects academic progress. With no secondary school within 30 kilometres, delivery combines a digital spine, weekend contact sessions in the village and project work mentored remotely by interns — piloted in month three and reviewed in month six [verify enrolment, network coverage and device access].

## 6.3 Interns — ten, in two cohorts

Five engineering interns from VNIT Nagpur deliver the platform work packages (section 5.3), design the field data workflow and mentor students. Five management interns from IIM Nagpur, from month seven, prepare business models, the six bankable project documents, the blended-finance structure and financial-closure routes. Rolling cohorts with overlap, written procedures and the open repository carry continuity when interns rotate.

## 6.4 The income objective

The cadre structure aims at incremental household income aligned to the Lakhpati Didi objective — household income of one lakh rupees or more, sustained across four seasons or cycles. The status cannot be claimed at the end of year one; the year-one indicator is that households are on track against a baseline established before training begins. Each cadre has a post-grant income line: fees for insemination and collection work; solar facilitation and gas tariffs; producer-organisation margin; water services contracted by the panchayat; and nutrition-garden material and programme incentives [verify].

# 7. The year-one output: the GP-IIP

The central output of year one is Katlabodi’s Gram Panchayat Integrated Investment Plan — a ten-year plan that converges the six projects, with cost estimates, finance routes and indicators. It is prepared in the form required for the Viksit Gram Panchayat Plan under VB-G RAM G, which came into force on 1 July 2026 and focuses works on water security, rural infrastructure, livelihood infrastructure and extreme-weather mitigation. The panchayat must prepare that plan in any case; the grant ensures it is climate-integrated, evidence-based and bankable.

The planning sequence runs from community landscape assessment, to community priority, to permissible VB-G RAM G work, to climate and natural-resource outcome, to convergence requirement, to indicator — so that community priorities are not lost because they do not match a work title. The grant pays for what a civil-works list cannot: participatory mapping, hydrogeological assessment, biodiversity survey, climate-risk analysis, technical design and monitoring. VB-G RAM G and other schemes then pay for the works.

Alongside the GP-IIP, year one produces six project documents to bankable standard, a trained and certified local cadre, a deployed and openly licensed platform, a working hub site, and a verified evidence base.

# 8. From hub to State: the scaling pathway

| Tier | When | Scale | What is proven or built |
| --- | --- | --- | --- |
| Hub — Katlabodi | Year 1 (this grant) | 3 villages; 717 people | The model works: cadre, platform, baselines, hub site, GP-IIP and six bankable projects |
| Cluster — Katol block | Years 2–3 | 186 villages; about 1.64 lakh people; 37,710 households (Census 2011) [verify number of Gram Panchayats] | The model works across panchayats: trainer cascade; hub nursery supplies the cluster; block assets such as milk chilling and a dung-based biogas plant; landscape and watershed plans; carbon aggregation |
| State — Maharashtra | Years 3–5 | 358 talukas | A proven, costed and replicable model, ready for adoption through the State’s VGPP process |

How it scales. Every Gram Panchayat must prepare a VGPP, so the State already has a channel to every village; a climate-integrated VGPP template proven in Katol travels through it. DEVTech is open source, so each new panchayat is a configuration, not a build. Sakhi cadre members become master trainers for neighbouring panchayats, working with the State Rural Livelihoods Mission. Watersheds, grazing, forest fire and carbon aggregation need planning above the panchayat, which the cluster tier provides.

Gates. The cluster tier begins when the hub shows cadre income trajectories against baseline, a water budget maintained by the panchayat, the platform in routine use, and the GP-IIP adopted as the VGPP. The State tier is supported by cost per Gram Panchayat, documented from the cluster.

# 9. What each partner gains

| Partner | Value | Ask |
| --- | --- | --- |
| Solar Industries India Limited (CSR) | A drought response with results fully attributable within twelve months; alignment with Schedule VII — hunger, health and drinking water; education and livelihoods; women; environmental sustainability and agroforestry; rural development; support for BRSR reporting on environment and inclusive development | Year-one grant |
| Gram Panchayat and community | Income, fodder and water security; assets and data owned by the panchayat; a VGPP prepared for it | Resolutions, land allocation, Biodiversity Management Committee |
| District administration and State (Rural Development, VB-G RAM G) | A climate-integrated VGPP template; drought relief delivered through local capacity; panchayat-level evidence against the Drought Management Code | Convergence of works; adoption of the template |
| State Rural Livelihoods Mission | Certified cadres and a trainer cascade built on its architecture | Certification linkage; cluster roll-out |
| National Biodiversity Authority and Maharashtra State Biodiversity Board | Biodiversity treated as infrastructure; a working BMC with a living digital People’s Biodiversity Register | Recognition as a pilot; technical guidance |
| Maharashtra Forest Department (JICA forest-management project) | A forest-fringe field pilot combining local knowledge, a community cadre and digital tools | Pilot site; joint training of frontline staff and cadre |
| NABARD, National Medicinal Plants Board, National AYUSH Mission | Bankable medicinal agroforestry and Wadi-type projects, prepared and verified | Scheme finance from year two |
| VNIT Nagpur and IIM Nagpur | A live laboratory; IPBES-named data gaps addressed | Intern cohorts; academic supervision |
| Market partners (Ayurvan, Manas Ayurved) | Graded, traceable medicinal produce from a women-led supply base | Anchor and second-buyer offtake |

# 10. Governance, roles and safeguards

| Party | Role |
| --- | --- |
| Ayurvan Foundation | Implementation lead and grant recipient; conservation and ecological expertise; community mobilisation; accountable to the donor for delivery and utilisation; holder of capital assets created by the grant, with the Gram Panchayat |
| UrjaGram Innovations | USDF framework; DEVTech deployment; project development and monitoring; coordination with government; GP-IIP preparation; carbon accounting; reporting; contributes platform and specialist expertise in kind |
| Gram Panchayat Katlabodi | Land identification and allocation; approvals; scheme identification; self-help group support; data fiduciary; adoption of the GP-IIP as its VGPP |
| VNIT Nagpur and IIM Nagpur | Academic supervision of the intern cohorts |

## 10.1 Safeguards

- No asset without a management plan — operator, maintenance responsibility, fee model where relevant and indicators identified before approval.

- No extraction without recharge — groundwater and irrigation works follow a water budget and hydrogeological assessment.

- No plantation without survival standards — local, climate-suitable, mixed species, with survival and diversity measured for at least three to five years.

- No restoration without community rights — commons and forest-fringe land require Gram Panchayat participation, tenure clarity and benefit-sharing.

- Equity — selection rules adopted before selection; the share of benefit reaching the bottom half of livestock owners is reported.

- Reach — cadre places fixed at 2/1/1 by village; siting tested against access from all three villages; coverage reported by village.

- Academic protection, grievance and financial governance — the tutor protects academic progress; a grievance mechanism is published in Marathi; grant funds are held in a dedicated, audited project account.

## 10.2 Compliance matters

- Registration of the implementing agency for CSR funding and its tax-exemption registrations.

- Gram Panchayat resolutions on execution authority, site allocation, data fiduciary designation and constitution or activation of the Biodiversity Management Committee.

- Capital assets created from the grant vest in Ayurvan Foundation or the Gram Panchayat, as the CSR Rules require [verify Rule 7(4)].

- Project addenda to the tripartite agreement: funds flow, carbon rights, intellectual property, data ownership, asset vesting and term.

- Administrative overheads within the limit prescribed under the CSR Rules; the measurement framework supports an independent impact assessment where required.

- Any surplus from revenue-bearing components is retained within the programme.

# 11. Year-one milestones

| Months | Milestones |
| --- | --- |
| 1–3 (Dec–Feb) | Project account opened; Gram Panchayat resolutions adopted; cadre and students selected; tutor and project manager engaged; engineering interns onboarded. Drought-state baselines: livestock re-verification, household income, water mapping, health and nutrition. Drought contingency plan for fodder and water. Hub-site preparation and nursery set-up begin. Katlabodi instance configuration. Student model piloted |
| 4–6 (Mar–May) | Baselines published. Recharge and repair works through VB-G RAM G convergence. Nursery stock raised. Livestock and energy cadres trained. VanaGram OS and water modules under construction. Identity spine live. Land, species and PBR assessment complete. Health gap analysis submitted to the district. Student model reviewed |
| 7–9 (Jun–Aug) | Monsoon planting at the hub site. Management interns onboarded. All five cadres trained; certification linkage established. Data protection layer and Marathi consent live. Public repository published. Net-zero module and carbon baseline delivered. Draft project documents circulated |
| 10–12 (Sep–Nov) | GP-IIP adopted as the VGPP. Six project documents at bankable standard. Finance routes opened. Cluster roll-out plan and aggregation structure designed; carbon rights resolved. Year-one evaluation. Platform administration handed to the panchayat |

# 12. Measurement framework

Year-one indicators are outputs within the programme’s control and are what the donor is accountable for. Ten-year indicators are outcomes that depend on the finance year one unlocks, and are shown so that the donor can see what the contribution leads to.

## 12.1 Year-one indicators

| Indicator | Baseline | Year-one target |
| --- | --- | --- |
| Women trained and certified across five cadres | 0 | 20 — four per cadre, distributed 2/1/1 |
| Students enrolled and retained; tutor engaged | 0 | 20 students; 12 months |
| Interns engaged with archived deliverables | 0 | 10 |
| Drought contingency plan for fodder and water | None | Adopted by the Gram Panchayat |
| Livestock register re-verified | 94% of volume entered 2017–22 | Households with four or more animals re-verified |
| Household income baseline for cadre households | None | 20 households |
| Health and nutrition baseline; gap analysis to district | None | Complete and submitted |
| Hub site: nursery and demonstration plantation | None | Nursery operating; about 5 ha planted; survival monitored |
| People’s Biodiversity Register | [verify current status] | Updated and maintained on VanaGram OS |
| Platform instance with five cadre modules | 0 | 5 modules configured |
| Public repository under AGPL-3.0 | Not published | By month 9 |
| GP-IIP adopted as VGPP; project documents at bankable standard | 0 | 1 plan; 6 documents |
| Panchayat carbon account and baseline | No inventory | Complete; carbon rights recorded in an addendum |
| Cluster roll-out plan and aggregation structure | None | Designed and costed |

## 12.2 Ten-year and scaling indicators

| Area | Indicator | Direction of travel |
| --- | --- | --- |
| Agroforestry | Area under cultivation; women earning; share sold processed; woody survival | From zero to an operating value chain and a permanent asset |
| Water | Groundwater trend; water budget maintained by the panchayat | From unmeasured to measured stability |
| Livestock | Live register; milk pooled; price per litre; share of income to bottom half; methane per litre | From concentrated, informal and unrecorded to organised and widening |
| Energy and carbon | Clean cooking; solar installed; net carbon balance | From no inventory to an audited balance |
| Health | Dietary diversity; local food share; entitlement enrolment; unmet need | From seasonal deficit to local sufficiency and full enrolment |
| Net-zero | Panchayats configured; credits verified; revenue shared | From one panchayat to a block cohort |
| Scaling | Gram Panchayats with climate-integrated VGPPs; master trainers certified; cost per Gram Panchayat | Katol cluster by year 3; State-ready model by year 5 |
| Cross-cutting | Self-help group households sustaining ₹1 lakh income | Aligned to Lakhpati Didi |

The scaling indicators make a grant to a panchayat of 717 people rational: without them the donor funds one village; with them, the donor funds a replication method, with Katlabodi as the proving ground.

# 13. What year one unlocks

| Project | Convergence and finance routes | Year-one precondition |
| --- | --- | --- |
| Agroforestry | National Medicinal Plants Board and National AYUSH Mission; NABARD Wadi and Tribal Development Fund; VB-G RAM G nursery and plantation works; JICA forest-management pilot | Hub site; land and species assessment; PBR; trained cadre; offtake arrangement |
| Water | VB-G RAM G water-security and extreme-weather works; State watershed and drought works; Finance Commission tied grants; micro-irrigation schemes | Water budget; hydrogeological assessment; prioritised works list; contingency plan |
| Livestock | National livestock and cattle missions; sexed semen and breeding support; Katol block milk chilling and biogas under the State CBG policy | Verified register; trained cadre; facility design; collection arrangement |
| Energy | Community biogas and solar programmes; PM Surya Ghar; blended and corporate finance | Plant design and siting; operator training plan |
| Health and nutrition | National Health Mission and Ayushman Bharat; Mission Saksham Anganwadi and Poshan 2.0; school feeding; National AYUSH Mission [verify] | Baseline; gap analysis; Poshan Sakhi cadre; local-food protocol |
| Net-zero platform | Voluntary carbon standards; domestic offset mechanism as it widens; climate finance and aggregation vehicles | Configured platform; baseline; aggregation structure; rights resolved |

# 14. Principal risks

| Risk | Consequence | Mitigation |
| --- | --- | --- |
| Drought recurs in 2027 | Hub-site yields and incomes fall; cadre confidence drops | Drought-tolerant species; water budget before extraction; contingency plan; stress-tested finances (Annex D) |
| Sanction later than January 2027 | Dry-season works and monsoon planting slip a year | Target start December 2026; baselines and contingency planning front-loaded |
| Elite capture of benefits | A few families absorb the gains | Selection rules adopted before selection; equity share reported |
| Project 1 operating shortfall in year two | Hub site under-maintained after the grant | Nursery sales to the cluster and VB-G RAM G works; convergence finance from year two |
| Student component fails on geography | Attrition; education objective missed | Blended delivery piloted and reviewed; connectivity verified |
| Cadre roles end with the grant | Capacity dissipates | Post-grant income lines; government certification |
| Delay in scheme convergence | Year two stalls | Several routes per project; documents ready before application windows |
| Data protection failure | Harm to residents; reputational exposure | Panchayat as fiduciary; consent, access and retention before release |
| No applicable carbon methodology; aggregation below viable volume | Balance sheet without revenue | Registry-agnostic design; voluntary standards; cluster aggregation; open source |
| Carbon claimed without real reduction | Reputational damage to all parties | Conservative defaults; volumes never merged; independent verification |
| Health access depends on facilities outside the panchayat | Health objective half met | Gap analysis addressed to the district; enrolment as the year-one deliverable |

# 15. Budget

Human capital and Project 1 are costed. Platform and programme-management lines are being developed with VNIT Nagpur and local stakeholders so that unit costs reflect local conditions. The detailed Project 1 model is in the accompanying workbook.

| Ref | Component | Amount (₹) |
| --- | --- | --- |
| A | Human capital | 24,30,000 |
| A1 | Cadre training — 20 women across five cadres; 10 days a month at ₹500 a day for 12 months, including certification linkage | 12,00,000 |
| A2 | Student programme — materials, connectivity, contact sessions and classroom smart devices | 3,00,000 |
| A3 | Tutor — 12 months at ₹10,000 a month | 1,20,000 |
| A4 | Intern stipends — 5 engineering at ₹5,000 a month for 12 months; 5 management at ₹7,000 a month for 6 months | 5,10,000 |
| A5 | Master training, exposure visits and cascade training | 3,00,000 |
| B | Platform customisation and deployment — B1 to B8 (section 5.3) | [to be finalised] |
| C | Baselines and project preparation — delivered by the trained cadre, mentored by UrjaGram | Nil |
| D | Project 1 — hub nursery and demonstration site (Annex D) | 1,81,46,200 |
| D1 | Capital expenditure — site preparation, nursery structures, water source, drip irrigation, fencing, power, equipment, establishment staff | 1,65,06,000 |
| D2 | Year-one operating shortfall (operation and maintenance less year-one sales) | 16,40,200 |
| E | Programme management — project manager, monitoring and reporting, audit | [to be finalised] |
|  | Costed to date (A + D) | 2,05,76,200 |
|  | Total grant sought | [on completion of B and E] |

## 15.1 Contributions in kind — not charged to the grant

| Contribution | Contributed by |
| --- | --- |
| Platform development to date — four components, three in production | UrjaGram Innovations |
| Specialist domain expertise; baseline and project-preparation mentoring | UrjaGram Innovations |
| Local conservation expertise and community mobilisation | Ayurvan Foundation |
| Land, approvals and convening | Gram Panchayat Katlabodi |
| Academic supervision of the intern cohorts | VNIT Nagpur and IIM Nagpur |

# 16. Open items for partner discussion

| # | Item | Owner |
| --- | --- | --- |
| 1 | Costing of platform (B) and programme-management (E) lines | UrjaGram, VNIT Nagpur, Ayurvan |
| 2 | Confirmation of Katol’s inclusion in the drought Government Resolution | UrjaGram |
| 3 | Implementing agency’s CSR and tax-exemption registrations | Ayurvan Foundation |
| 4 | Gram Panchayat resolutions — execution authority, hub-site allocation, data fiduciary, BMC | Gram Panchayat |
| 5 | Land classification of the three Rithi villages; management status of the 416 ha of forest | Gram Panchayat |
| 6 | Basis for Project 1 nursery revenue; overlap between establishment staff and year-one operating cost | Ayurvan Foundation |
| 7 | Enrolment of the twenty students; network coverage and device access | Ayurvan Foundation |
| 8 | Mapping of each cadre to its recognised equivalent | UrjaGram Innovations |
| 9 | Project addenda — funds flow, carbon rights, IP, data, asset vesting, term | All partners |
| 10 | Hosting and maintenance from year two; Project 1 year-two operating cost | All partners |
| 11 | Confirmation of IIM Nagpur engagement; health convergence routes | All partners |
| 12 | Number of Gram Panchayats in Katol block, for the cluster plan | UrjaGram Innovations |

# Annexures

- A — Registration and compliance documents of the implementing agency

- B — Tripartite Memorandum of Agreement dated 13 July 2026

- C — Resolutions of the Gram Panchayat for the CSR proposal

- D — Project 1: Biodiversity and medicinal agroforestry — the Katlabodi hub site, with financial model (Project1_Agroforestry_Finances_v2.xlsx)

- E — Project briefs for the six projects

## References

IPBES (2024). Summary for Policymakers of the Thematic Assessment Report on the Interlinkages among Biodiversity, Water, Food and Health. IPBES secretariat, Bonn. DOI 10.5281/zenodo.13850289.

The Times of India, September 2026: “Maha declares drought in 265 talukas or 3/4ths of state”; “Kharif crop gone, rabi in doubt: Why Maha farmers are distressed” (24 September 2026).

Viksit Bharat – Guarantee for Rozgar and Ajeevika Mission (Gramin) Act, 2025, in force from 1 July 2026. World Bank, World Development Report 2026. Census of India 2011, village directory.

Prepared by Ayurvan Foundation with UrjaGram Innovations Pvt Ltd and Gram Panchayat Katlabodi. Discussion draft — not for external circulation.